## Itinerary
# | Component | Category | Layer | Status | Priority | Phase | Mine from | Notes
1 | Button | Actions | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
2 | Links | Actions | 1 Base | Partial | P2 | 2 Depth | HSBC Figma / WCAG | Have base set; external-link / new-window variant still to add (CA-6).
3 | Quick-actions | Actions | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
4 | Segmented (View-options) | Actions | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
5 | Icon button | Actions | 1 Base | Gated | P0 | 0 Have | MD3 / Carbon / Ant | Reviewed + gated 2026-07-20 — Mono button/* ladder, real sprite glyphs, icon-015 4.5:1
6 | Split button | Actions | 1 Base | Gap | P3 | 3 Scale | Ant / Carbon | Nice-to-have.
7 | FAB (mobile) | Actions | 1 Base | Gap | P3 | 3 Scale | MD3 | Mobile floating action.
8 | Text input | Inputs & forms | 1 Base | Gated | P0 | 0 Have | — | input-fields, gated.
9 | Search field | Inputs & forms | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
10 | Select | Inputs & forms | 1 Base | Gated | P0 | 0 Have | — | dropdown, gated.
11 | Checkbox / Radio / Switch | Inputs & forms | 1 Base | Gated | P0 | 0 Have | — | selection-controls, gated.
12 | Slider | Inputs & forms | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
13 | Form layout + validation | Inputs & forms | 1 Base | Gap | P1 | 1 Foundations | Carbon / Ant / GOV.UK | Field groups, inline + form-level errors. Biggest single gap.
14 | Date picker | Inputs & forms | 1 Base | Gap | P1 | 1 Foundations | Ant / Carbon / MD3 | Core banking input.
15 | Date-range picker | Inputs & forms | 1 Base | Gap | P1 | 1 Foundations | Ant / Carbon | Statements / reporting periods.
16 | Time picker | Inputs & forms | 1 Base | Gap | P1 | 1 Foundations | Ant / MD3 | Payments scheduling.
17 | Number / currency (amount) input | Inputs & forms | 1 Base | Gap | P1 | 1 Foundations | Fintech (Stripe) / Ant | Amount entry with formatting; banking-critical.
18 | File upload / dropzone | Inputs & forms | 1 Base | Gap | P1 | 1 Foundations | Ant / Carbon / Untitled | Document upload journeys.
19 | OTP / PIN / secure entry | Inputs & forms | 1 Base | Gap | P1 | 1 Foundations | Fintech (Plaid/Stripe) | Banking auth; generic systems lack this.
20 | Textarea | Inputs & forms | 1 Base | Gap | P1 | 1 Foundations | Ant / Carbon / MD3 | Multi-line input.
21 | Combobox / autocomplete | Inputs & forms | 1 Base | Gap | P2 | 2 Depth | Ant / Untitled | Type-ahead select.
22 | Multi-select | Inputs & forms | 1 Base | Gap | P2 | 2 Depth | Ant / Carbon | Chips-in-field selection.
23 | Tags input | Inputs & forms | 1 Base | Gap | P2 | 2 Depth | Ant / Untitled | Free-entry token field.
24 | Range slider | Inputs & forms | 1 Base | Gap | P3 | 3 Scale | Ant / MD3 | Dual-handle.
25 | Rating | Inputs & forms | 1 Base | Gap | P3 | 3 Scale | Ant | Star / score input.
26 | Cascader / tree-select | Inputs & forms | 1 Base | Gap | P3 | 3 Scale | Ant | Hierarchical select.
27 | Transfer (dual list) | Inputs & forms | 1 Base | Gap | P3 | 3 Scale | Ant | Move-between lists.
28 | Tabs | Navigation | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
29 | Tab-bar | Navigation | 1 Base | Gated | P0 | 0 Have | — | Mobile bottom nav, gated.
30 | Breadcrumbs | Navigation | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
31 | Pagination | Navigation | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
32 | Nav / Menu | Navigation | 1 Base | Gated | P0 | 0 Have | — | navigations, gated.
33 | Dropdown menu | Navigation | 1 Base | Gated | P0 | 0 Have | — | dropdown, gated.
34 | Stepper (interactive) | Navigation | 1 Base | Gap | P1 | 1 Foundations | Ant / Carbon / MD3 | Progress-tracker is display-only; this drives multi-step flows.
35 | Command palette / global search | Navigation | 1 Base | Gap | P2 | 2 Depth | Untitled / Tailwind | Power-user search.
36 | Sidebar / nav rail | Navigation | 1 Base | Gap | P2 | 2 Depth | Tailwind / Untitled | Desktop app frame nav.
37 | Anchor / scrollspy | Navigation | 1 Base | Gap | P3 | 3 Scale | Ant | In-page section nav.
38 | Back-to-top | Navigation | 1 Base | Gap | P3 | 3 Scale | Ant | Long-page utility.
39 | Table | Data display | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
40 | List-items | Data display | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
41 | Cards | Data display | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated (first Code Connect spoke).
42 | Account-card | Data display | 1 Base | Gated | P0 | 0 Have | — | Fintech; gated.
43 | Summary | Data display | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
44 | Accordion | Data display | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
45 | Tags | Data display | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
46 | Badge | Data display | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
47 | Status-indicator | Data display | 1 Base | Gated | P0 | 0 Have | — | RAG chips, gated.
48 | Avatar | Data display | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
49 | Reorder | Data display | 1 Base | Gated | P0 | 0 Have | — | Gated (portfolio-interactions testbed).
50 | Progress-tracker (display) | Data display | 1 Base | Gated | P0 | 0 Have | — | Display-only; interactive Stepper is the gap.
51 | Data grid (sort/filter/select/edit) | Data display | 1 Base | Gap | P1 | 1 Foundations | Carbon / Ant / AG-Grid | Data-dense tables; drives most fintech screens.
52 | Stat / metric card | Data display | 1 Base | Gap | P1 | 1 Foundations | Tailwind / Untitled | Only a util today; promote to gated component.
53 | Charts / data-viz kit | Data display | 1 Base | Gap | P1 | 1 Foundations | dataviz skill / Carbon | Bar / line / donut / sparkline. Fitness tests invented these.
54 | Empty state | Data display | 1 Base | Gap | P1 | 1 Foundations | Untitled / Tailwind | No-data / first-run screens.
55 | KPI / trend tile | Data display | 1 Base | Gap | P2 | 2 Depth | Tailwind / Untitled | Metric + delta + spark.
56 | Timeline / activity feed | Data display | 1 Base | Gap | P2 | 2 Depth | Ant / Untitled | Transaction history pattern.
57 | Avatar group | Data display | 1 Base | Gap | P2 | 2 Depth | Untitled / MD3 | Stacked avatars.
58 | Tree | Data display | 1 Base | Gap | P3 | 3 Scale | Ant / Carbon | Hierarchical data.
59 | Calendar | Data display | 1 Base | Gap | P3 | 3 Scale | Ant / MD3 | Full month view (distinct from date picker).
60 | Carousel | Data display | 1 Base | Gap | P3 | 3 Scale | Ant / Untitled | Rotating content.
61 | QR code | Data display | 1 Base | Gap | P3 | 3 Scale | Fintech | Payments / onboarding.
62 | Notifications | Feedback & status | 1 Base | Gated | P0 | 0 Have | — | Persistent; gated.
63 | Modal / Dialog | Feedback & status | 1 Base | Partial | P1 | 1 Foundations | HSBC Figma (mI8hvIkV…) | Have confirm/alert dialog; true modals + lightboxes (desktop+mobile) to add.
64 | Tooltip | Feedback & status | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
65 | Spinner (Loading) | Feedback & status | 1 Base | Gated | P0 | 0 Have | — | loading-indicator, gated.
66 | Confirmation | Feedback & status | 1 Base | Partial | P2 | 2 Depth | HSBC Figma | Mobile success gated; desktop dialog-style variant to add.
67 | Countdown timer | Feedback & status | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
68 | Alert / inline callout | Feedback & status | 1 Base | Gap | P1 | 1 Foundations | Carbon / Ant / GOV.UK | Already logged; inline + form-level messaging.
69 | Toast / snackbar | Feedback & status | 1 Base | Gap | P1 | 1 Foundations | MD3 / Ant | Transient; distinct from persistent Notifications.
70 | Drawer / side sheet | Feedback & status | 1 Base | Gap | P1 | 1 Foundations | Ant / MD3 / Untitled | Slide-in panel for filters/detail.
71 | Popover | Feedback & status | 1 Base | Gap | P1 | 1 Foundations | Ant / Untitled | Rich anchored content; distinct from Tooltip.
72 | Skeleton loader | Feedback & status | 1 Base | Gap | P1 | 1 Foundations | Ant / MD3 / Untitled | Perceived-performance placeholder.
73 | Banner | Feedback & status | 1 Base | Gap | P2 | 2 Depth | Untitled / Tailwind | Page-level persistent message.
74 | Progress bar (linear/circular) | Feedback & status | 1 Base | Gap | P2 | 2 Depth | Ant / MD3 | Determinate progress.
75 | Popconfirm | Feedback & status | 1 Base | Gap | P2 | 2 Depth | Ant | Inline confirm-in-place.
76 | Divider | Layout & containers | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
77 | Header | Layout & containers | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
78 | Hero | Layout & containers | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
79 | Eyebrow | Layout & containers | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
80 | Action-bar | Layout & containers | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
81 | Footer | Layout & containers | 1 Base | Gap | P2 | 2 Depth | Tailwind / Untitled | Incl. doormat / mega-footer.
82 | Grid / stack utilities | Layout & containers | 1 Base | Gap | P2 | 2 Depth | Tailwind / MUI | Layout primitives.
83 | Splitter / resizable | Layout & containers | 1 Base | Gap | P3 | 3 Scale | Ant | Resizable panes.
84 | Video-player | Media & identity | 1 Base | Gated | P0 | 0 Have | — | Reviewed + gated.
85 | Icon system | Media & identity | 1 Base | Gated | P0 | 0 Have | — | Dynamic-weight; some glyph gaps logged (_ICON-GAPS).
86 | Brand mark / logo | Media & identity | 1 Base | Gap | P1 | 1 Foundations | HSBC brand assets | Official asset; needed for shells/auth screens.
87 | Image / media block | Media & identity | 1 Base | Partial | P3 | 3 Scale | Untitled / Tailwind | Partial today.
88 | RAG / status chips | Fintech-specific | 1 Base | Gated | P0 | 0 Have | — | status-indicator, gated.
89 | Amount / currency display + money format | Fintech-specific | 1 Base | Gap | P1 | 1 Foundations | Fintech (Stripe/Wise) | Money formatting primitive; a true differentiator.
90 | Account selector / masked account chip | Fintech-specific | 1 Base | Partial | P1 | 1 Foundations | Fintech / Account-card | Partial via Account-card; promote a selector chip.
91 | Transaction / ledger row | Fintech-specific | 1 Base | Partial | P2 | 2 Depth | Fintech (Monzo/Stripe) | Statement/ledger line item.
92 | Statement / document row | Fintech-specific | 1 Base | Partial | P2 | 2 Depth | Fintech | Downloadable document row.
93 | Payment-card visual | Fintech-specific | 1 Base | Gap | P2 | 2 Depth | Fintech (Stripe/Apple) | Card face render.
94 | Coverage / runway bar | Fintech-specific | 1 Base | Gap | P2 | 2 Depth | Fintech (own) | Cash-runway meter (fitness tests invented this).
95 | Standing-order / mandate row | Fintech-specific | 1 Base | Gap | P3 | 3 Scale | Fintech | Recurring-payment row.
96 | Limits meter | Fintech-specific | 1 Base | Gap | P3 | 3 Scale | Fintech | Spend/transfer limit gauge.
97 | App shell — top / stacked nav | Shells (Layer 2) | 2 Shell | Gap | P2 | 3 Scale | Tailwind UI (~23 shells) | Frame content lives in.
98 | App shell — side nav | Shells (Layer 2) | 2 Shell | Gap | P2 | 3 Scale | Tailwind UI | Desktop app frame.
99 | App shell — multi-column | Shells (Layer 2) | 2 Shell | Gap | P2 | 3 Scale | Tailwind UI | List + detail frame.
100 | App shell — split | Shells (Layer 2) | 2 Shell | Gap | P3 | 3 Scale | Tailwind UI | Two-pane.
101 | App shell — focused / full-page | Shells (Layer 2) | 2 Shell | Gap | P3 | 3 Scale | Tailwind UI | Auth / wizard frame.
102 | App shell — doormat (mega-footer) nav | Shells (Layer 2) | 2 Shell | Gap | P3 | 3 Scale | Tailwind UI | Marketing frame.
103 | App shell — nav rail | Shells (Layer 2) | 2 Shell | Gap | P3 | 3 Scale | Tailwind UI / MD3 | Compact icon rail.
104 | Template — dashboard | Templates (Layer 2) | 2 Template | Gap | P2 | 3 Scale | Tailwind / Untitled | Composes from stat/chart/grid bases.
105 | Template — list / index | Templates (Layer 2) | 2 Template | Gap | P2 | 3 Scale | Tailwind / Untitled | Table/list + filter bar.
106 | Template — detail | Templates (Layer 2) | 2 Template | Gap | P2 | 3 Scale | Tailwind / Untitled | Record detail view.
107 | Template — create / edit form | Templates (Layer 2) | 2 Template | Gap | P2 | 3 Scale | Tailwind / Untitled | Needs Form base first.
108 | Template — settings | Templates (Layer 2) | 2 Template | Gap | P3 | 3 Scale | Tailwind / Untitled | Preferences layout.
109 | Template — multi-step wizard | Templates (Layer 2) | 2 Template | Gap | P2 | 3 Scale | Tailwind / Untitled | Needs Stepper base first.
110 | Template — empty | Templates (Layer 2) | 2 Template | Gap | P3 | 3 Scale | Untitled | Composes Empty-state base.
111 | Template — error (404 / 500) | Templates (Layer 2) | 2 Template | Gap | P3 | 3 Scale | Tailwind / Untitled | Error pages.
112 | Template — auth (login / register / OTP) | Templates (Layer 2) | 2 Template | Gap | P2 | 3 Scale | Tailwind / Untitled | Needs OTP + brand-mark bases.
113 | Template — report | Templates (Layer 2) | 2 Template | Gap | P3 | 3 Scale | Fintech / Untitled | Printable statement/report.
114 | Template — confirmation | Templates (Layer 2) | 2 Template | Gap | P3 | 3 Scale | Untitled | Composes Confirmation base.
115 | Lock-up — page headers (tabs/actions/breadcrumb/meta) | Lock-ups (Layer 2) | 2 Lock-up | Gap | P2 | 3 Scale | Tailwind (25 header variants) | The Untitled multiplier lives here.
116 | Lock-up — section headings | Lock-ups (Layer 2) | 2 Lock-up | Gap | P3 | 3 Scale | Tailwind | Configured heading rows.
117 | Lock-up — card headers | Lock-ups (Layer 2) | 2 Lock-up | Gap | P3 | 3 Scale | Tailwind | Card-top arrangements.
118 | Lock-up — hero variants | Lock-ups (Layer 2) | 2 Lock-up | Gap | P3 | 3 Scale | Tailwind / Untitled | Hero configurations.
119 | Lock-up — stats band | Lock-ups (Layer 2) | 2 Lock-up | Gap | P3 | 3 Scale | Tailwind | Row of stat tiles.
120 | Lock-up — filter / toolbar bar | Lock-ups (Layer 2) | 2 Lock-up | Gap | P2 | 3 Scale | Tailwind / Untitled | Above tables/lists.
121 | Lock-up — footer / doormat | Lock-ups (Layer 2) | 2 Lock-up | Gap | P3 | 3 Scale | Tailwind | Mega-footer.
122 | Lock-up — CTA | Lock-ups (Layer 2) | 2 Lock-up | Gap | P3 | 3 Scale | Tailwind / Untitled | Call-to-action band.
123 | Lock-up — feature grid | Lock-ups (Layer 2) | 2 Lock-up | Gap | P3 | 3 Scale | Tailwind / Untitled | Feature tiles.
124 | Per-component variant matrices | Lock-ups (Layer 2) | 2 Variant | Gap | P3 | 3 Scale | Untitled UI (10k+ variants) | Every base × emphasis/size/state/density — the number multiplier to 200–300.

## Summary
Apollo component library — itinerary summary
Total items in itinerary | 124
Layer 1 (base components) | 96
Layer 2 (shells / templates / lock-ups) | 28
Already gated (have) | 38
Partial (extend existing) | 7
Gap (to build) | 79
P1 — reliability-critical | 23
P2 — common | 30
P3 — nice-to-have | 33
Phase 1 · Foundations | 23
Phase 2 · Depth | 19
Phase 3 · Scale | 44
With per-component variants + Layer 2 multiplier → 200–300 item catalogue